## PRICE SUBMITTAL SCHEDULE
SURFSIDE PARK - PRICE SUBMITTAL SCHEDULE OF VALUES
Item | Description | Estimated Quantity | Unit of Measure | Unit Cost | Total (Qty x Unit Cost)
GENERAL CONDITIONS
1 | General Conditions | 1 | LS | $ | $
|  |  |  | SUBTOTAL | $
MOBILIZATION & DEMOLITION
2 | Mobilization / Demobilization | 1 | LS | $ | $
3 | Construction Fencing (8' Screened Chain Link) | 663 | LF | $ | $
4 | Maintenance of Traffic (MOT) | 1 | LS | $ | $
5 | Erosion Control | 1 | LS | $ | $
6 | Clear & Grub | 1 | AC | $ | $
7 | Demolition | 1 | LS | $ | $
|  |  |  | SUBTOTAL | $
EARTHWORK
8 | Import, Place and Compact Fill Material | 1290 | CY | $ | $
9 | Final Grading | 43530 | SF | $ | $
|  |  |  | SUBTOTAL | $
LANDSCAPING
10 | Existing Tree Protection | 47 | EA | $ | $
11 | Large Tree Transplant | 7 | EA | $ | $
12 | Small Tree / Palm Transplant | 10 | EA | $ | $
13 | Tree Removal | 1 | EA | $ | $
14 | Tree Pruning | 1 | LS | $ | $
TREES
15 | Cassia bakeriana / Pink Shower Tree | 1 | EA | $ | $
16 | Canella winterana / Cinnamon bark | 1 | EA | $ | $
17 | Tabebuia caraiba / Yellow Trumpet Tree | 1 | EA | $ | $
PALMS
18 | Sabal palmetto / Sabal Palm | 15 | EA | $ | $
19 | Thrinax radiata / Florida Thatch palm | 11 | EA | $ | $
SHRUBS / GRASSES
20 | Borrichia arborescens / Sea Oxeye Daisy | 19 | EA | $ | $
21 | Byrsonima lucida / Locust Berry | 25 | EA | $ | $
22 | Chrysobalanus icaco 'Horizontalis' / Horizontal Cocoplum | 280 | EA | $ | $
23 | Ficus microcarpa 'Green Island' / Ficus Green Island | 235 | EA | $ | $
24 | Hamelia patens / Firebush | 5 | EA | $ | $
25 | Lantana involucrata / White Lantana - Wild Sage | 8 | EA | $ | $
26 | Muhlenbergia capillaris / Pink Muhly Grass | 35 | EA | $ | $
27 | Philodendron 'Rojo Congo' / Rojo Congo Philodendron | 11 | EA | $ | $
28 | Psychotria ligustrufolia / Bahama Coffee | 112 | EA | $ | $
29 | Psychotria nervosa / Wild Coffee | 115 | EA | $ | $
30 | Serenoa repens 'Silver' / Silver Saw Palmetto | 30 | EA | $ | $
31 | Strelitzia reginae / Bird of Paradise | 3 | EA | $ | $
GROUNDCOVERS
32 | Dietes vegeta / White African Iris | 37 | EA | $ | $
33 | Ernodea litoralis / Beach Creeper | 39 | EA | $ | $
34 | Lantana 'Gold' / Dwarf Gold Lantana | 70 | EA | $ | $
35 | Microsorum scolopendria / Wart Fern | 366 | EA | $ | $
36 | Nephrolepis exaltata / Boston Fern | 137 | EA | $ | $
37 | Peperomia obtusifolia / Green Peperomia | 214 | EA | $ | $
38 | Spartina bakeri / Sand Cordgrass | 55 | EA | $ | $
39 | Tripsacum dactyloides / Fakahatchee Grass | 18 | EA | $ | $
40 | Tripsacum floridanum / Dwarf Fakahatchee Grass | 117 | EA | $ | $
41 | Zamia pumila / Coontie | 118 | EA | $ | $
42 | Sod - Bermuda grass - Celebration or Latitude 36 (with 4" soil blanket) | 14017 | SF | $ | $
43 | Fiber Reinforced Sod - Bermuda grass - Celebration or Latitude 36 (with specified subbase system) | 1430 | SF | $ | $
44 | Mulch | 1 | LS | $ | $
45 | Jute Mesh | 800 | SF | $ | $
46 | Root Barriers | 418 | LF | $ | $
47 | Aluminum Edging | 690 | LF | $ | $
|  |  |  | SUBTOTAL | $
IRRIGATION
48 | Landscape Irrigation (Including controls & electrical) | 1 | LS | $ | $
|  |  |  | SUBTOTAL | $
PAVING
49 | Concrete Sidewalk, in ROW | 972 | SF | $ | $
50 | Concrete Sidewalk, Vehicular Crossing, in ROW | 110 | SF | $ | $
51 | Concrete with Shell Aggregate - Park Pathways | 2661 | SF | $ | $
52 | Stabilized Coquina - at Shaded Plaza & Kayak Path | 3431 | SF | $ | $
53 | Poured in Place Rubberized Surface - at Playground | 5851 | SF | $ | $
54 | Engineered Wood Fiber - at Exercise Equipment (509 sf x 8" depth) | 12.5 | CY | $ | $
55 | Type D Concrete Curb | 482 | LF | $ | $
|  |  |  | SUBTOTAL | $
PARK FEATURES
56 | Kayak Launch (includes platform, ramp & floating dock) | 1 | LS | $ | $
57 | Concrete Basketball Court | 4588 | SF | $ | $
58 | Basketball Goals | 2 | EA | $ | $
59 | Metal Picket Fence | 455 | LF | $ | $
60 | Sports Netting | 240 | LF | $ | $
61 | Water Mister | 1 | EA | $ | $
62 | Drinking Fountain | 1 | EA | $ | $
63 | Lightning Detection | 1 | LS | $ | $
|  |  |  | SUBTOTAL | $
SITE UTILITIES / PLUMBING
64 | Site Storm Drainage (includes bedding stone) | 1 | LS | $ | $
65 | Site Water Supply | 1 | LS | $ | $
66 | Site Sanitary Sewer | 1 | LS | $ | $
67 | Drinking Fountain & Mister - Plumbing only | 1 | EA | $ | $
|  |  |  | SUBTOTAL | $
SITE LIGHTING / ELECTRICAL
68 | Pathway Lighting (including foundations & wiring) | 4 | EA | $ | $
69 | Basketball Court Lighting (including foundations & wiring) | 2 | EA | $ | $
70 | Multipurpose Field Lighting (including foundations) | 4 | EA | $ | $
71 | Duplex WP Electric Outlets | 6 | EA | $ | $
|  |  |  | SUBTOTAL | $
SITE FURNITURE
72 | BENCH-EMAU SOLO (EMS456) | 4 | EA | $ | $
73 | CHAISE CHAIRS-RIVAGE (RVA251) | 2 | EA | $ | $
74 | STOOL-STACK (STC212) | 2 | EA | $ | $
75 | TABLE-STACK (STC410) | 2 | EA | $ | $
76 | TABLE-TABLY (TBL421) | 1 | EA | $ | $
77 | BENCH-VERA SOLO (LVS211) | 2 | EA | $ | $
78 | BENCH-EMAU (EM251) | 2 | EA | $ | $
79 | CHAIR-STACK (STC257) | 6 | EA | $ | $
80 | BENCH-STACK (STC255) | 2 | EA | $ | $
81 | BENCH- VERA SOLO (LVS510) | 1 | EA | $ | $
82 | BENCH- VERA SOLO MODULAR (LVS22)(LVS50)(LVS52) | 1 | EA | $ | $
83 | BIKE RACK-EDGETYRE (STE210) | 7 | EA | $ | $
84 | TRASH & RECYCLE RECEPTACLE: CRYSTAL (CS331X) | 2 | EA | $ | $
85 | FREIGHT | 1 | LS | $ | $
86 | SALES TAX | 1 | LS | $ | $
87 | FURNITURE - INSTALL | 1 | LS | $ | $
|  |  |  | SUBTOTAL | $
PLAYGROUND & FITNESS EQUIPMENT
88 | BERLINER - CLOUD 9 | 1 | EA | $ | $
89 | BERLINER - SWINGO 2.2 | 1 | EA | $ | $
90 | BERLINER - FREERIDE | 1 | EA | $ | $
91 | BERLINER - WINDRIDER | 1 | EA | $ | $
92 | BERLINER - COMBINATION 1 | 1 | EA | $ | $
93 | BERLINER - COMBINATION 2 | 1 | EA | $ | $
94 | BERLINER - BOO | 1 | EA | $ | $
95 | BERLINER - 4'-0" FAST LANE SLIDE (HDPE) | 1 | EA | $ | $
96 | AUSTRALIAN PINE / SINKER CYPRESS TREE STUMPS | 1 | LS | $ | $
97 | FREIGHT | 1 | LS | $ | $
98 | SALES TAX | 1 | LS | $ | $
99 | PLAYGROUND EQUIPMENT - INSTALL | 1 | LS | $ | $
100 | FITNESS EQUIPMENT | 1 | LS | $
101 | FREIGHT | 1 | LS | $ | $
102 | SALES TAX | 1 | LS | $ | $
103 | EXERCISE EQUIPMENT - INSTALL | 1 | LS | $ | $
|  |  |  | SUBTOTAL | $
ARCHITECTURE - COMMUNITY BUILDING (LEED GOLD)
104 | Two Story Community Building | 1 | LS | $ | $
105 | Solar Panels on Community Building | 1 | LS | $ | $
|  |  |  | SUBTOTAL | $
GENERAL CONTRACTOR
106 | GC Overhead | 1 | LS | $ | $
107 | GC Profit | 1 | LS | $ | $
108 | Bond / Insurance | 1 | LS | $ | $
109 | Contingency / Escalation Allowance | 1 | LS | $ | $
|  |  |  | SUBTOTAL | $
| TOTAL PRICE SUBMITTAL AMOUNT (ITEMS 1-109) |  |  |  | $
All quantities are approximate. Contractor shall be responsible to verify all quantities and inform the Town of Surfside of any discrepancies. In addition, please refer to RFQ for additional special conditions.
|  | BIDDER: |  |  | INITIALS: